## 📋 Instructions
EFL — Executive Scorecard
PURPOSE | This workbook collects all raw data needed to calculate the 8 scorecard metrics and automatically computes status (Green/Yellow/Red).
HOW TO USE | 1. Each month/sprint: open the relevant DATA INPUT sheet and enter blue-text cells only.
2. The SCORECARD sheet pulls all computed metrics automatically — do not edit it.
3. The Formulas sheet is a reference for all metric definitions and thresholds.
COLOR CODING | Blue = Input cells (you fill these) ¦ Black = Formula (auto-calculated) ¦ Green = Cross-sheet link
SHEETS
💵 Financial | Enter monthly cost actuals, planned spend, story points, and EAC updates.
🏃 Sprints | AUTO-CALCULATED - Pull all data from 'Team Sprints Input' sheet and 'Team Median Input'
🏃 Team Sprints Input | Enterp per-sprint commitment and completion counts for each delivery teams.
Team Median Input | Enterp per-sprint median cycle time (Dev, QA and Overall) for each delivery teams.
🐛 Quality | Enter defect counts by severity per release; enter rework effort and first time pass rate
📊 Scorecard | AUTO-CALCULATED. All 7 metrics with RAG status and 3-month/3-sprint trend.
📐 Formulas | Reference sheet with all metric definitions and threshold rules.
FREQUENCY | Financial & Quality = Monthly. Sprint metrics = Per sprint + monthly rollup.
BASELINE | Set baselines in the yellow-highlighted cells on the Financial and Sprint sheets on first use.

## 📊 Scorecard
EXECUTIVE SCORECARD — Auto-Calculated Summary
All values pull automatically from the data input sheets. Do not edit this sheet.
Metric | Jan | Feb | Mar | Apr | May | Jun | Threshold / Target
💰 FINANCIAL HEALTH
EAC vs SOW Budget % | 88.42% | 91.36% | 80.15% | 82.03% | 75.29% |  | 🟢 ≤100% 🟡 100–105% 🔴 >105%
EAC Status | 🟢 Green | 🟢 Green | 🟢 Green | 🟢 Green | 🟢 Green |  | Auto from Financial sheet
Monthly Burn Variance % | -4.759% | -4.049% | -12.75% | -9.66% | -12.14% |  | 🟢 ≤±5% 🟡 ±5–10% 🔴 >±10%
Burn Variance Status | 🟢 Green | 🟢 Green | 🔴 Red | 🟡 Yellow | 🔴 Red |  | Auto from Financial sheet
Cost per SP — Stories Delivered($) | 2281.4432 | 979.3937 | 880.6069 | 835.6597 | 811.3905 |  | 🟢 Stable/↓ 🟡 ↑5–10% 🔴 ↑>10%
Cost/SP Status | NIL | 🟢 Green | 🟢 Green | 🟢 Green | 🟢 Green |  | Auto from Financial sheet
3-Mo Rolling Avg Cost/SP ($) | NIL | 979.3937 | 920.1216 | 892.3375 | 872.4333 |  | Trend indicator
🏃 DELIVERY PREDICTABILITY & FLOW
Commitment Reliability — Monthly Avg | 100% | 97.94% | 105.6% | 86.23% | 42.05% | 0% | 🟢 ≥85% 🟡 75–84% 🔴 <75%
CR Status | 🟢 Green | 🟢 Green | 🟢 Green | 🟢 Green | 🔴 Red | 0 | Auto from Sprints sheet
Cycle Time Median | 5.3 | 4.5288 | 5.1825 | 4.5175 | 4.7346 | 0 | 🟢 Stable/↓ 🟡 ↑ up to 10% 🔴 ↑>10%
Cycle Time Status | 🟢 Green | 🟢 Green | 🟢 Green | 🟢 Green | 🟢 Green |  | Auto from Sprints sheet
🐛 QUALITY & REWORK
Defect Leakage % — Monthly |  |  | 17.65% | 1.523% | 2.586% |  | 🟢 ≤10% 🟡 11–15% 🔴 >15%
Leakage Status |  |  | 🔴 Red | 🟢 Green | 🟢 Green |  | Auto from Quality sheet
Rework Ratio — Monthly | 3.448% | 21.65% | 21.5% | 27.45% | 27.68% |  | Auto from Quality sheet
Rework Status | 🟢 Green | 🟡 Yellow | 🟡 Yellow | 🟡 Yellow | 🟡 Yellow |  | 🟢 ≤20% 🟡 21–30% 🔴 >30%
First Time Pass Rate |  |  | 86.36% | 82.6% | 82.62%
Status |  |  | 🟡 Yellow | 🔴 Red | 🔴 Red |  | >=95% : Green, >85% : Yellow, <=85% Red
📋 CURRENT MONTH SNAPSHOT — All Metrics at a Glance
Metric | Current Value | Target | Status | Remarks
EAC vs Budget | 75.29% | ≤100% | 🟢 Green | this is for May month
Monthly Burn Variance | -12.14% | ±5% | 🔴 Red | 3 Onsite positions removed (Lalitha, Anil, Nanda) and rest all PTOs
Cost/SP — Team | 811.3905 | 983 | 🟢 Green
Commitment Reliability | 42.05% | ≥85% | 🔴 Red | Overall red combining Q2 SP3, SP4 but SP2 commitment
Cycle Time (Median) | 4.7346 | 5.4 days | 🟢 Green
Prod Defect Leakage | 1.523% | ≤10% | 🟢 Green
Rework Ratio | 27.68% | ≤20% | 🟡 Yellow | this covers Q2 SP3 and Q2 SP4. Team 1 rework ratio was high 50%
FTPR | 82.62% | >=95% | 🔴 Red | May Q2 SP3 - 81%, SP4 - 92%. Team 2 had low FTPR consistently for both sprints
Note on F17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Release activities took priorities over sprint

## 💵 Financial
FINANCIAL DATA INPUT — Monthly
Blue cells = enter data. Black cells = auto-calculated. Update monthly.
SECTION A — Budget & EAC
Field | Jan | Feb | Mar | Apr | May | Jun | July |  | Notes
SOW Budget Target ($) | 471406 | 471406 | 471406 | 471406 | 471406 | 471406 |  |  | Enter SOW contract value
Estimate at Completion EAC ($) | 416796 | 430671 | 377817 | 386711 | 354940.5 |  |  |  | Enter latest EAC each month
EAC vs Budget % | 88.42% | 91.36% | 80.15% | 82.03% | 75.29% | 0% |  |  | Auto: EAC÷Budget
EAC Status | 🟢 Green | 🟢 Green | 🟢 Green | 🟢 Green | 🟢 Green | 🟢 Green |  |  | Auto: RAG threshold ≤100%/≤105%/>105%
SECTION B — Sprint Burn Variance (Exclude VM DM cost and Innova/ERIE cost)
Field | SP1 | SP2 | SP3 | SP4 | SP5 | SP6 | Q2 SP1 | Q2 SP2 | Q2 SP3 | Q2 SP4 | Q2 SP5 | Notes
Planned Monthly Spend ($) | 210800 | 210800 | 210800 | 210800 | 210800 | 210800 | 210800 | 192960 | 190960 | 190960 |  | Enter planned budget for given sprint | ERIE | Colton, John, Luke, Jacob, Marc, Jen, Erin, Matt, Sierra, Ryan, Mru
Actual Monthly Spend ($) | 200767 | 195257 | 209273 | 198914 | 182912 | 168949 | 182327 | 181744.6 | 170392 | 78673.3 |  | Enter actual spend | Innova | 4 onsite (2 Mendix + 1 Integration + 1 BA), 4 offshore (2 Mendix + 2 QA)
Burn Variance ($) | -10033 | -15543 | -1527 | -11886 | -27888 | -41851 | -28473 | -11215.4 | -20568 | -112286.7 |  | Auto: Actual−Planned
Burn Variance % | -4.759% | -7.373% | -0.7244% | -5.639% | -13.23% | -19.85% | -13.51% | -5.812% | -10.77% | -58.8% |  | Auto: Variance÷Planned
Burn Status | 🟢 Green | 🟡 Yellow | 🟢 Green | 🟡 Yellow | 🔴 Red | 🔴 Red | 🔴 Red | 🟡 Yellow | 🔴 Red | 🔴 Red |  | Auto: RAG ≤±5% / ≤±10% / >±10%
SECTION C — Cost per Story Point (Only VM)
Field | SP1 | SP2 | SP3 | SP4 | SP5 | SP6 | Q2 SP1 | Q2 SP2 | Q2 SP3 | Q2 SP4 | Q2 SP5 | Notes
Story Points Delivered (All 4 Teams) | 84 | 178 | 147 | 323 | 164 | 113 | 220 | 141 | 169 | 162 | 215 | Feature+story SP completed
Defect (bugs) SP Delivered (All 4 Teams) | 4 | 22 | 66 | 108 | 37 | 20 | 22 | 57 | 41 | 48 | 83 | Defect SP completed this month
Total SP (incl. Defects) | 88 | 200 | 213 | 431 | 201 | 133 | 242 | 198 | 210 | 210 | 298 | Auto: sum
Team Cost ($) (from Actual Burn) | 200767 | 195257 | 209273 | 198914 | 182912 | 168949 | 182327 | 181744.6 | 170392 | 78673.3 |  | Auto: links from Actual Spend above
Cost per SP — Stories Completed ($) | 2390.0833 | 1096.9494 | 1423.6259 | 615.8328 | 1115.3171 | 1495.1239 | 828.7591 | 1288.9688 | 1008.2367 | 485.6377 |  | Auto: Team Cost ÷ Stories SP
Cost per SP — Stories + Standalone Defects ($) | 2281.4432 | 976.285 | 982.5023 | 461.5174 | 910.01 | 1270.2932 | 753.4174 | 917.902 | 811.3905 | 374.6348 |  | Auto: Team Cost ÷ Total SP
Baseline Cost/SP — Team ($) | NIL | NIL | 983 | 983 | 983 | 983 | 983 | 983 | 983 | 983 |  | 🟡 Set once based on 2-3 Sprints
Team Cost/SP Status | 🟢 Green | 🟢 Green | 🟢 Green | 🟢 Green | 🟢 Green | 🔴 Red | 🟢 Green | 🔴 Red | 🟡 Yellow | 🟢 Green |  | Auto: RAG vs baseline ±10% (Variance <=10% Yellow, >10% Red)
3-Month Rolling Avg Cost/SP — Team ($) | NIL | 976.285 | 979.3937 | 806.7682 | 832.5787 | 920.1216 | 892.3375 | 895.9896 | 872.4333 | 785.595 |  | Auto: rolling 3-month avg (for trend reporting)
MONTHLY ROLLUP — Budget & EAC
Month | Budget | Actual | Variance ($) | Variance % | 3-Sprint Trend
January | 471406 | 416796 | 54610 | 88.42% | 🟢 Green
February | 942812 | 847467 | 95345 | 89.89% | 🟢 Green
March | 1414218 | 1225284 | 188934 | 86.64% | 🟢 Green
MONTHLY ROLLUP — Cost per Story Point
Month | Actual | Baseline | Variance % | Trend
January | 2281.4432 | NIL | #VALUE! | 🟢 Green
February | 979.3937 | 983 | -0.3669% | 🟢 Green
March | 880.6069 | 983 | -10.42% | 🟢 Green
April | 835.6597 | 983 | -14.99% | 🟢 Green
May | 811.3905 | 983 | -17.46% | 🟢 Green
Note on A7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What is spent so far
Note on C14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Offshore holiday on 1/26 i.e. $7,680
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This does not include team 1 points as they were into kanban
Note on C23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This includes team 1 points end of SP2.
Note on G26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Due to BRP, overall team delivered less points
Note on A27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to have Innova and ERIE cost for this baseline cost
Note on B29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This should be ignored as team 1 points not included here

## 🐛 Quality
QUALITY DATA INPUT — Monthly & Per Release
Enter defect data per release. Enter effort hours monthly. Status is auto-calculated.
SECTION A — Production Defect Leakage (Per Release) - 0–10% : Green 11–15% : Yellow, 15%> : Red
Formula: Prod Defect / All Defects X 100 ¦ Sev1=5× Sev2=3× Sev3=1×
Release / Feature | Month | Prod Defects Sev 1 (#) | Prod Defects Sev 2 (#) | Prod Defects Sev 3 (#) | Prod Defects Sev 4 (#) | Prod Defects Sev 5 (#) | Total Prod Defects | QA Defects | UAT Defects | Total Defects | Leakage % (auto) | Leakage Status
EEL STOLI Release | March | 0 |  |  | 2 | 1 | 3 | 17 | 0 | 17 | 17.65% | 🔴 Red
TUW Pilot | April |  | 1 | 3 | 5 |  | 9 | 573 | 18 | 591 | 1.523% | 🟢 Green
TUW 1.1 | May |  | 2 | 1 |  |  | 3 | 93 | 23 | 116 | 2.586% | 🟢 Green
SECTION B — Monthly Defect Leakage Rollup - 0–10% : Green 11–15% : Yellow, 15%> : Red
Month | Total Prod Defects | Total Pre-prod Defects | Leakage % | Status
March | 3 | 17 | 17.65% | 🔴 Red
April | 9 | 591 | 1.523% | 🟢 Green
May | 3 | 116 | 2.586% | 🟢 Green
SECTION C — Rework Ratio (Sprint and Monthly View) - <=20% : Green, <=30% : Yellow, >30% Red
Rework Ratio = Defect Effort in Points/ Total Completed Story Points × 100
Sprint ID | Month | Rework # (Standalone Bugs) | Total Completed | Rework Ratio | Status | Notes | Mitigation
Sprint 1 | January | 4 | 116 | 3.448% | 🟢 Green
Sprint 2 | February | 34 | 404 | 8.416% | 🟢 Green
Sprint 3 | February | 75 | 215 | 34.88% | 🔴 Red
Sprint 4 | March | 127 | 439 | 28.93% | 🟡 Yellow
Sprint 5 | March | 60 | 351 | 17.09% | 🟢 Green
Sprint 6 | March | 39 | 211 | 18.48% | 🟢 Green
Q2 Sprint 1 | April | 37 | 307 | 12.05% | 🟢 Green
Q2 Sprint 2 | April | 102 | 238 | 42.86% | 🔴 Red | The rework % increase due to Team 1 uncovering App Packet and Policy Packet form related defects | Coding/design errors - Solution lead of team 1 agreed to increase unit testing coverage
Q2 Sprint 3 | May | 61 | 300 | 20.33% | 🟡 Yellow | The rework % came down as more story points completed in this sprint
Q2 Sprint 4 | May | 90 | 257 | 35.02% | 🔴 Red | Team 1 primarily worked on Release 1.1 and 1.2 activities ( thus increasing the rework percentage) Team 2 also worked on more defects compared to previous sprint leading up to Final Expense Pilot release. Team 4 worked on more defects as well in this sprint.
Q2 Sprint 5 | June | 104 | 317 | 32.81% | 🔴 Red | Team 1 primarily worked on bugs as part of Release activities ( thus increasing the rework percentage) Team 2 also worked on more defects compared to previous sprint leading up to Final Expense Pilot release.
SECTION D — First Time Pass Rate- >=95% : Green, >85% : Yellow, <=85% Red
First Time Pass Rate = Total Stories with defects/ Total Completed Story Points × 100
Sprint ID | Month | Total Stories W/O defects | Total Stories Delivered | First Time Pass % | Status | Notes
Sprint 1 | January | 0 | 0 | #DIV/0! | #DIV/0!
Sprint 2 | February | 0 | 0 | #DIV/0! | #DIV/0!
Sprint 3 | February | 0 | 0 | #DIV/0! | #DIV/0!
Sprint 4 | March | 0 | 0 | #DIV/0! | #DIV/0!
Sprint 5 | March | 84 | 98 | 85.71% | 🟡 Yellow
Sprint 6 | March | 67 | 77 | 87.01% | 🟡 Yellow
Q2 Sprint 1 | April | 89 | 119 | 74.79% | 🔴 Red | Team 1 has only 51% FTPR in this sprint
Q2 Sprint 2 | April | 66 | 73 | 90.41% | 🟡 Yellow | Team 1 has 75% FTPR. Improvement due to 5 why analysis and mitigation actions, i.e. Additional Code Review and Unit testing Coverage. Team 2,3 & 4 also shown better results
Q2 Sprint 3 | May | 83 | 107 | 77.57% | 🔴 Red | Team 2 FTPR was 65% in this sprint, other teams were consistent. 5 Why results awaited.
Q2 Sprint 4 | May | 64 | 73 | 87.67% | 🟡 Yellow | FTPR improved to 79% for team 2, other teams were consistent
Q2 Sprint 5 | June | 81 | 102 | 79.41% | 🔴 Red | FTPR was 66% for team 2 and 68% for team 1, other teams were consistent | Enforce 5-Why ( Pending For team 1 & 2 from SP2)
SECTION E — In Sprint Automation
Team | SprintId | TOTAL STORY CARDS | Automatable Cards | Test Cards Actually Automated | Manually executed Cards | %Automated | Comments | Total Bugs
Team 1 | SP1 | 48 | 17(7(VAM)+10(Innova)) | 0 | 71 | 0 | Lack of Bandwidth due to pilot testing, 50% more Sprint cards delivered compared to average velocity | 23
Team 2 | SP1 | 16 | 7 | 5 | 12 | 71% | Able to achieve 71% insprint Automation | 1
Team 3 | SP1 | 17 | 2 | 1 | 24 | 50% | 50% achieved.As discussed with Karthik, release 1.1 related cards were automated | 7
Team 1 | SP2 | 16 | 7(2(VAM)+5(Innova)) | 2 | 87 | 28.57% | 28.57% achieved. As discussed with Karthik, only release 1.1 related cards were automated | 73
Team 2 | SP2 | 57 | 6 | 0 | 60 | 0% | Team had about 90% more story cards allocated than average in this sprint | 3
Team 3 | SP2 | 8 | 0 | 0 | 11 | NA |  | 3
Team-1 | SP3 | 20 | 0 | 0 | 28 | NA |  | 28
Team 2 | SP3 | 52 | 0 | 0 | 75 | NA |  | 23
Team 3 | SP3 | 19 | 2 | 0 | 21 | 0% | Lack of Bandwidth due to pilot testing , cross product testing,and sprint work | 3
Team-1 | SP4 | 29 | 0 | 0 | 82 | NA |  | 53
Team 2 | SP4 | 30 | 0 | 0 | 49 | NA |  | 19
Team 3 | SP4 | 4 | 2 | 0 | 5 | 0 | Lack of Bandwidth due to pilot testing , cross product testing,and sprint work | 1
Team-1 | SP5 | 29 | 14 | 10 | 4 | 71.43%
Team 2 | SP5 | 4 | 1 | 0 | 1 | 0% | Team was occupied with FE Release activities
Team 3 | SP5 | 23 | 4 | 0 | 4 | 0% | Team was occupied with 1.3 and Enterprise Release activities

## 🏃 Sprints
SPRINT DATA INPUT — Per Sprint
1. Commitment Reliability - Delivery Predictability, Overcommitment vs execution blockers 2. Cycle Time (Median) - How fast value is delivered and Team efficiency
SECTION A — Commitment Reliability (<75% - Red; >=75 to <85% - Yellow; >=85% - Green)
Sprint ID | Month | Stories Planned | Stories Defects Planned | Standalone Bugs Planned | Stories Completed | Story Defects Completed | Standalone Bugs Completed | Total Planned (Exclude Story defects) | Total Completed (Exclude Story defects) | Baseline Velocity | Completion % | CR Status | VM Completed Stories | VM Standalone Bugs Completed | Notes
Sprint 1 | January | 250 | 24 | 10 | 112 | 8 | 4 | 260 | 116 | 116 | 100% | 🟢 Green | 84 | 4
Sprint 2 | February | 588 | 40 | 64 | 370 | 41 | 34 | 652 | 404 | 316 | 127.8% | 🟢 Green | 178 | 22
Sprint 3 | February | 439 | 31 | 144 | 140 | 10 | 75 | 583 | 215 | 316 | 68.04% | 🔴 Red | 147 | 66
Sprint 4 | March | 605 | 17 | 158 | 312 | 43 | 127 | 763 | 439 | 316 | 138.9% | 🟢 Green | 323 | 108
Sprint 5 | March | 628 | 13 | 92 | 291 | 34 | 60 | 733 | 351 | 316 | 111.1% | 🟢 Green | 164 | 37
Sprint 6 | March | 520 | 26 | 64 | 172 | 23 | 39 | 610 | 211 | 316 | 66.77% | 🔴 Red | 113 | 20
Q2 Sprint 1 | April | 634 | 12 | 59 | 270 | 57 | 37 | 705 | 307 | 316 | 97.15% | 🟢 Green | 220 | 22
Q2 Sprint 2 | April | 648 | 13 | 145 | 136 | 11 | 102 | 806 | 238 | 316 | 75.32% | 🟡 Yellow | 141 | 57
Q2 Sprint 3 | May | 586 | 5 | 108 | 207 | 32 | 61 | 699 | 300 | 140 | 42.92% | 🔴 Red | 169 | 41
Q2 Sprint 4 | May | 485 | 11 | 128 | 147 | 20 | 90 | 624 | 257 | 140 | 41.19% | 🔴 Red | 162 | 48
Q2 Sprint 5 | June | 397 | 9 | 133 | 185 | 28 | 104 | 539 | 317 | 140 | 58.81% | 🔴 Red | 215 | 83
Sprint 6 | July | [6 empty] | 0 | 0
Sprint 7 | August
MONTHLY ROLLUP — Commitment Reliability (Stable, Improving and Declining)
Month | Sprints in Month | Avg Completion % | Monthly CR Status | 3-Sprint Trend
January | 1 | 100% | 🟢 Green | (need 3mo)
February | 2 | 97.94% | 🟢 Green | (need 3mo)
March | 3 | 105.6% | 🟢 Green | ↑ Improving
April | 2 | 86.23% | 🟢 Green | ↑ Improving
May | 2 | 42.05% | 🔴 Red | → Stable
SECTION B — Cycle Time (Median) - Baseline=0% - Green; Baseline <=10% - Yellow; Baseline >10%- Red
Cycle Time (Development → Testing → Review → Done) = Start Date → Done Date (days). Enter median for the sprint from JIRA
Sprint ID | Month | Median Cycle Time (days) | Baseline Cycle Time | Δ vs Baseline | Δ% vs Baseline | CT Status
Sprint 1 | January | 5.3 | 5.4 | -0.1 | -1.852% | 🟢 Green
Sprint 2 | February | 5.335 | 5.4 | -0.065 | -1.204% | 🟢 Green
Sprint 3 | February | 3.7225 | 5.4 | -1.6775 | -31.06% | 🟢 Green
Sprint 4 | March | 4.3325 | 5.4 | -1.0675 | -19.77% | 🟢 Green
Sprint 5 | March | 5.7075 | 5.4 | 0.3075 | 5.694% | 🟡 Yellow
Sprint 6 | March | 6.0325 | 5.4 | 0.6325 | 11.71% | 🔴 Red
Q2 Sprint 1 | April | 4.685 | 5.4 | -0.715 | -13.24% | 🟢 Green
Q2 Sprint 2 | April | 4.35 | 5.4 | -1.05 | -19.44% | 🟢 Green
Q2 Sprint 3 | May | 4.1667 | 5.4 | -1.2333 | -22.84% | 🟢 Green
Q2 Sprint 4 | May | 5.3025 | 5.4 | -0.0975 | -1.806% | 🟢 Green
Q2 Sprint 5 | June | 5.1 | 5.4 | -0.3 | -5.556% | 🟢 Green
Sprint 6 | June
SECTION B — Development Cycle Time (Median) - Baseline=0% - Green; Baseline <=10% - Yellow; Baseline >10%- Red
Cycle Time (Development → Testing)
Sprint ID | Month | Median Cycle Time (days) | Baseline Cycle Time | Δ vs Baseline | Δ% vs Baseline | CT Status
Sprint 1 | January | 5.2 | 5.2 | 0 | 0% | 🟢 Green
Sprint 2 | February | 3.765 | 5.2 | -1.435 | -27.6% | 🟢 Green
Sprint 3 | February | 2.785 | 5.2 | -2.415 | -46.44% | 🟢 Green
Sprint 4 | March | 3.01 | 5.2 | -2.19 | -42.12% | 🟢 Green
Sprint 5 | March | 5.03 | 5.2 | -0.17 | -3.269% | 🟢 Green
Sprint 6 | March | 4.1575 | 5.2 | -1.0425 | -20.05% | 🟢 Green
Q2 Sprint 1 | April | 4.15 | 5.2 | -1.05 | -20.19% | 🟢 Green
Q2 Sprint 2 | April | 2.78 | 5.2 | -2.42 | -46.54% | 🟢 Green
Q2 Sprint 3 | May | 3.4 | 5.2 | -1.8 | -34.62% | 🟢 Green
Q2 Sprint 4 | May | 4.2375 | 5.2 | -0.9625 | -18.51% | 🟢 Green
Q2 Sprint 5 | June | 3.7 | 5.2 | -1.5 | -28.85% | 🟢 Green
Sprint 12
Sprint 13
Sprint 14
SECTION B — QA Cycle Time (Median) - Baseline=0% - Green; Baseline <=10% - Yellow; Baseline >10%- Red
Cycle Time (Testing → Acceptance)
Sprint ID | Month | Median Cycle Time (days) | Baseline Cycle Time | Δ vs Baseline | Δ% vs Baseline | CT Status
Sprint 1 | January | 3.2 | 3.2 | 0 | 0% | 🟢 Green
Sprint 2 | February | 3.1225 | 3.2 | -0.0775 | -2.422% | 🟢 Green
Sprint 3 | February | 1.24 | 3.2 | -1.96 | -61.25% | 🟢 Green
Sprint 4 | March | 1.6925 | 3.2 | -1.5075 | -47.11% | 🟢 Green
Sprint 5 | March | 2.4575 | 3.2 | -0.7425 | -23.2% | 🟢 Green
Sprint 6 | March | 3.675 | 3.2 | 0.475 | 14.84% | 🔴 Red
Q2 Sprint 1 | April | 2.425 | 3.2 | -0.775 | -24.22% | 🟢 Green
Q2 Sprint 2 | April | 2.125 | 3.2 | -1.075 | -33.59% | 🟢 Green
Q2 Sprint 3 | May | 2.5 | 3.2 | -0.7 | -21.88% | 🟢 Green
Q2 Sprint 4 | May | 1.835 | 3.2 | -1.365 | -42.66% | 🟢 Green
Q2 Sprint 5 | June | 1.9 | 3.2 | -1.3 | -40.63% | 🟢 Green
Sprint 12
Sprint 13
Sprint 14

## 📐 Formulas
METRIC DEFINITIONS, FORMULAS & THRESHOLDS — Reference
Metric | Formula | 🟡 Green | 🟡 Yellow | 🔴 Red | Frequency / Notes
EAC vs SOW Budget | EAC ÷ SOW Budget Target × 100 | ≤ 100% | 100–105% | > 105% | Monthly. Top drivers required if Yellow/Red.
Monthly Sprint Burn Variance | (Actual Spend − Planned Spend) ÷ Planned Spend × 100 | ≤ ±5% | ±5–10% | > ±10% | Monthly. Log drivers: rework, delays, scope, staffing.
Cost per Story Point — Story Points Delivered | Team Cost ($) ÷ Story Points Delivered (Team SP only) | Stable or ↓ vs baseline | ↑ 5–10% vs baseline | ↑ >10% vs baseline | Monthly; rolling 3-month avg for trend. Baseline = first full sprint month.
Cost per Story Point — Defects delivered | Team Cost ($) ÷ Total SP (Team SP + Defect SP) | Stable or ↓ vs baseline | ↑ 5–10% vs baseline | ↑ >10% vs baseline | Monthly; defect work sized and included. Same baseline as Team.
Commitment Reliability | Total Completed (Stories+Defects+Bugs) ÷ Total Committed × 100 | ≥ 85% | 75–84% | < 75% | Per sprint + monthly rollup + 3-sprint trend.
Cycle Time (Median) | Median(Done Date − In-Progress) across all cards in period | Stable or ↓ vs baseline | ↑ up to 10% vs baseline | ↑ > 10% vs baseline | Per sprint + monthly rollup + 3-sprint trend. Start = first In Progress.
Production Defect Leakage (Severity-Weighted) | Total Prod Defects ÷ All Pre-Prod Defects × 100 | ≤ 10% | 11–15% | > 15% | Monthly + per release/feature. Measured post-deployment.
Rework Ratio | (Story and Standalone Bug Fix Effort ÷ Total Points Delivered) × 100 | ≤ 20% | 21–30% | > 30% | Monthly with rolling trend.
First Time Pass Rate | (Stories Completed w/o any defects ÷ Total stories delivered) × 100 | ≥ 95% | ≥ 85% | < 85% | Monthly with rolling trend.
KEY ASSUMPTIONS & NOTES
Baseline setting | Set the Cost/SP and Cycle Time baselines ONCE in the yellow-highlighted cells on first use. These persist as the reference for all RAG calculations.
Defect sizing | Defects must be estimated in story points BEFORE the sprint to be included in Cost/SP program calculation and sprint commitment.
Severity weighting | Use weights in Quality sheet if we decide to use them for severity scales.
Rework Effort | Capture Story Defects and Standalone Bug Fix Points/counts ÷ Total Story Points in JIRA tool for accurate Rework Ratio.
Cycle time source | Pull median cycle time from JIRA (Control Charts). Exclude blocked time if used for any reason

## Team Sprints Input
Team Wise Sprint Input
Sprint ID | Team | Sprint Start Date | Sprint End Date | Month | Stories Planned | Sprint Defects Planned | Standalone Bugs Planned | Story Points Completed | Story Defects Completed | Standalone Bugs Completed | Total Planned | Total Completed | Baseline Velocity | Rework Ratio | Comments
Sprint 1 | Team 1 | 2026-01-07 | 2026-01-20 | January | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
Sprint 1 | Team 2 | 2026-01-07 | 2026-01-20 | January | 48 | 13 | 0 | 30 | 5 | 0 | 48 | 30 | 45 | 0% | Lot of cards spilled over to pending testing and defects
Sprint 1 | Team 3 | 2026-01-07 | 2026-01-20 | January | 120 | 8 | 10 | 34 | 1 | 4 | 130 | 38 | 36 | 10.53% | All testing pending cards due to CSEI-11111 defect .Net Update Status Types testing was blocked. Save Token for Org Blocked due to CoreSuite not available with the functionality. COA tiles cards testing was blocked due to Experience Team misconfigured files in .net
Sprint 1 | Team 4 | 2026-01-07 | 2026-01-20 | January | 82 | 3 | 0 | 48 | 2 | 0 | 82 | 48 | 35 | 0% | Few are CIM related cards and few are reports which are still in analysis phase
Sprint 2 | Team 1 | 2026-01-21 | 2026-02-03 | February | 352 | 33 | 50 | 260 | 28 | 26 | 402 | 286 | 200 | 9.091%
Sprint 2 | Team 2 | 2026-01-21 | 2026-02-03 | February | 63 | 5 | 2 | 56 | 9 | 2 | 65 | 58 | 45 | 3.448%
Sprint 2 | Team 3 | 2026-01-21 | 2026-02-03 | February | 104 | 2 | 12 | 36 | 3 | 6 | 116 | 42 | 36 | 14.29% | Due to CSEI-11111 defect .Net Update Status Types testing was blocked CSEI-10456 defect blocked few mendix cards for organization tokenid Payment Center .Net cards were blocked due to Policy Inquiry API schema mismatch for PreActive OneTime GuestPayment - New Work in Payment Centerweb, MDM - Policy Status issues identified at last moment
Sprint 2 | Team 4 | 2026-01-21 | 2026-02-03 | February | 69 | 0 | 0 | 18 | 1 | 0 | 69 | 18 | 35 | 0% | Spill over mostly data suit reports
Sprint 3 | Team 1 | 2026-02-04 | 2026-02-17 | February | 206 | 20 | 113 | 53 | 2 | 52 | 319 | 105 | 200 | 49.52%
Sprint 3 | Team 2 | 2026-02-04 | 2026-02-17 | February | 61 | 7 | 4 | 35 | 8 | 4 | 65 | 39 | 45 | 10.26% | Due to testing spillover and review pending
Sprint 3 | Team 3 | 2026-02-04 | 2026-02-17 | February | 83 | 0 | 26 | 16 | 0 | 18 | 109 | 34 | 36 | 52.94% | Due to CSEI-11111 defect .Net Update Status Types testing was blocked.
Sprint 3 | Team 4 | 2026-02-04 | 2026-02-17 | February | 89 | 4 | 1 | 36 | 0 | 1 | 90 | 37 | 35 | 2.703%
Sprint 4 | Team 1 | 2026-02-18 | 2026-03-03 | March | 322 | 2 | 132 | 142 | 19 | 104 | 454 | 246 | 200 | 42.28%
Sprint 4 | Team 2 | 2026-02-18 | 2026-03-03 | March | 80 | 11 | 7 | 69 | 13 | 7 | 87 | 76 | 45 | 9.211%
Sprint 4 | Team 3 | 2026-02-18 | 2026-03-03 | March | 91 | 3 | 17 | 56 | 6 | 14 | 108 | 70 | 36 | 20% | Integration cards were spilled due to dependency on CSEI-7531. still not delivered Bene related mendix cards are spilled due to integration card dependency which are planned in SP5
Sprint 4 | Team 4 | 2026-02-18 | 2026-03-03 | March | 112 | 1 | 2 | 45 | 5 | 2 | 114 | 47 | 35 | 4.255% | Data suite Report cards and cards related for Fund file are spilled over due to pending requirement
Sprint 5 | Team 1 | 2026-03-04 | 2026-03-17 | March | 369 | 3 | 62 | 194 | 25 | 43 | 431 | 237 | 200 | 18.14%
Sprint 5 | Team 2 | 2026-03-04 | 2026-03-17 | March | 75 | 8 | 9 | 39 | 4 | 9 | 84 | 48 | 45 | 18.75%
Sprint 5 | Team 3 | 2026-03-04 | 2026-03-17 | March | 91 | 1 | 21 | 28 | 1 | 8 | 112 | 36 | 36 | 22.22%
Sprint 5 | Team 4 | 2026-03-04 | 2026-03-17 | March | 93 | 1 | 0 | 30 | 4 | 0 | 93 | 30 | 35 | 0%
Sprint 6 | Team 1 | 2026-03-18 | 2026-03-31 | March | 281 | 19 | 43 | 73 | 11 | 25 | 324 | 98 | 200 | 25.51% | BRP for multiple days. Reinstatement and conversion which are less priority cards are spilled over.
Sprint 6 | Team 2 | 2026-03-18 | 2026-03-31 | March | 93 | 7 | 3 | 49 | 7 | 2 | 96 | 51 | 45 | 3.922% | Cards are spilled over due to Status not getting updated
Sprint 6 | Team 3 | 2026-03-18 | 2026-03-31 | March | 68 | 0 | 18 | 13 | 4 | 12 | 86 | 25 | 36 | 48% | BRP was there for 2 days. Team had tempus issues multiple times so 3 defects belong to it. Status cards are blocked due to CoreSuite issues. Token ID, RNID company cards defects are fixed at the end of the sprint by Team 1.
Sprint 6 | Team 4 | 2026-03-18 | 2026-03-31 | March | 78 | 0 | 0 | 37 | 1 | 0 | 78 | 37 | 35 | 0%
Q2 Sprint 1 | Team 1 | 2026-04-01 | 2026-04-14 | April | 308 | 8 | 38 | 115 | 45 | 26 | 346 | 141 | 200 | 18.44%
Q2 Sprint 1 | Team 2 | 2026-04-01 | 2026-04-14 | April | 116 | 4 | 2 | 52 | 11 | 2 | 118 | 54 | 45 | 3.704%
Q2 Sprint 1 | Team 3 | 2026-04-01 | 2026-04-14 | April | 113 | 0 | 18 | 57 | 0 | 8 | 131 | 65 | 36 | 12.31%
Q2 Sprint 1 | Team 4 | 2026-04-01 | 2026-04-14 | April | 97 | 0 | 1 | 46 | 1 | 1 | 98 | 47 | 35 | 2.128%
Q2 Sprint 2 | Team 1 | 2026-04-15 | 2026-04-28 | April | 325 | 1 | 121 | 35 | 6 | 90 | 446 | 125 | 200 | 72% | most of the defects were related to forms
Q2 Sprint 2 | Team 2 | 2026-04-15 | 2026-04-28 | April | 143 | 11 | 13 | 47 | 4 | 8 | 156 | 55 | 45 | 14.55% | Team worked on more defects leading up to Final Expense Pilot release
Q2 Sprint 2 | Team 3 | 2026-04-15 | 2026-04-28 | April | 112 | 0 | 10 | 24 | 1 | 3 | 122 | 27 | 36 | 11.11%
Q2 Sprint 2 | Team 4 | 2026-04-15 | 2026-04-28 | April | 68 | 1 | 1 | 30 | 0 | 1 | 69 | 31 | 35 | 3.226%
Q2 Sprint 3 | Team 1 | 2026-04-29 | 2026-05-12 | May | 260 | 0 | 76 | 37 | 2 | 35 | 336 | 72 | 35 | 48.61%
Q2 Sprint 3 | Team 2 | 2026-04-29 | 2026-05-12 | May | 164 | 4 | 26 | 86 | 24 | 23 | 190 | 109 | 35 | 21.1% | Team worked on more defects leading up to Final Expense Pilot release
Q2 Sprint 3 | Team 3 | 2026-04-29 | 2026-05-12 | May | 83 | 0 | 6 | 34 | 4 | 3 | 89 | 37 | 35 | 8.108%
Q2 Sprint 3 | Team 4 | 2026-04-29 | 2026-05-12 | May | 79 | 1 | 0 | 50 | 2 | 0 | 79 | 50 | 35 | 0%
Q2 Sprint 4 | Team 1 | 2026-05-13 | 2026-05-26 | May | 209 | 0 | 94 | 67 | 14 | 66 | 303 | 133 | 35 | 49.62% | Majorly worked on Release 1.1 and 1.2 activities
Q2 Sprint 4 | Team 2 | 2026-05-13 | 2026-05-26 | May | 137 | 11 | 26 | 57 | 6 | 18 | 155 | 75 | 35 | 24% | Team worked on more defects leading up to Final Expense Pilot release
Q2 Sprint 4 | Team 3 | 2026-05-13 | 2026-05-26 | May | 91 | 0 | 3 | 13 | 0 | 1 | 94 | 14 | 35 | 7.143% | Mendix cards are blocked due to 1125 UWPro Notes issues, Integration card are blocked, simulate premium doesnt suffice requirements
Q2 Sprint 4 | Team 4 | 2026-05-13 | 2026-05-26 | May | 48 | 0 | 5 | 10 | 0 | 5 | 53 | 15 | 35 | 33.33% | Team worked on more defects in this sprint. File Integration cards had 1 issues ,also 2 issues with external team (CIM team) . File integration cards spilled over due to time taken in analysis and coordination
Q2 Sprint 5 | Team 1 | 2026-05-27 | 2026-06-09 | June | 128 | 4 | 100 | 58 | 10 | 83 | 228 | 141 | 35 | 58.87% | Team worked on more bugs when compared to previous sprints as part of recent releases hance the rework ratio increases
Q2 Sprint 5 | Team 2 | 2026-05-27 | 2026-06-09 | June | 95 | 3 | 22 | 62 | 17 | 17 | 117 | 79 | 35 | 21.52% | Team worked on more defects leading up to Final Expense Pilot release
Q2 Sprint 5 | Team 3 | 2026-05-27 | 2026-06-09 | June | 106 | 2 | 11 | 34 | 1 | 4 | 117 | 38 | 35 | 10.53%
Q2 Sprint 5 | Team 4 | 2026-05-27 | 2026-06-09 | June | 68 | 0 | 0 | 31 | 0 | 0 | 68 | 31 | 35 | 0%
|  | Sprint ID | Team 1 | Team 2 | Team 3 | Team 4
|  | Sprint 1 | NA | 0% | 10.53% | 0%
|  | Sprint 2 | 9.091% | 3.448% | 14.29% | 0%
|  | Sprint 3 | 49.52% | 10.26% | 52.94% | 2.703%
|  | Sprint 4 | 42.28% | 9.211% | 20% | 4.255%
|  | Sprint 5 | 18.14% | 18.75% | 22.22% | 0%
|  | Sprint 6 | 25.51% | 3.922% | 48% | 0%
|  | Q2 Sprint 1 | 18.44% | 3.704% | 12.31% | 2.128%
|  | Q2 Sprint 2 | 72% | 14.55% | 11.11% | 3.226%
|  | Q2 Sprint 3 | 48.61% | 21.1% | 8.108% | 0%
|  | Q2 Sprint 4 | 49.62% | 24% | 7.143% | 33.33%
Note on H8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No point assigned to bugs

## VAM Team Sprint-CostperSprint
Sprint ID | Team | Sprint Start Date | Sprint End Date | Month | Stories Completed | Story Defects Completed | Standalone Bugs Completed | Total Completed | Total Developers
Sprint 1 | Team 1 | 2026-01-07 | 2026-01-20 | January | 0 | 0 | 0 | 0
Sprint 1 | Team 2 | 2026-01-07 | 2026-01-20 | January | 21 | 5 | 0 | 21 | 4
Sprint 1 | Team 3 | 2026-01-07 | 2026-01-20 | January | 34 | 1 | 4 | 38
Sprint 1 | Team 4 | 2026-01-07 | 2026-01-20 | January | 25 | 2 | 0 | 25
Sprint 2 | Team 1 | 2026-01-21 | 2026-02-03 | February | 67 | 23 | 14 | 81
Sprint 2 | Team 2 | 2026-01-21 | 2026-02-03 | February | 42 | 9 | 2 | 44 | 4
Sprint 2 | Team 3 | 2026-01-21 | 2026-02-03 | February | 36 | 3 | 6 | 42
Sprint 2 | Team 4 | 2026-01-21 | 2026-02-03 | February | 11 | 1 | 0 | 11
Sprint 3 | Team 1 | 2026-02-04 | 2026-02-17 | February | 22 | 2 | 43 | 65
Sprint 3 | Team 2 | 2026-02-04 | 2026-02-17 | February | 25 | 8 | 4 | 29 | 4
Sprint 3 | Team 3 | 2026-02-04 | 2026-02-17 | February | 16 | 0 | 18 | 34
Sprint 3 | Team 4 | 2026-02-04 | 2026-02-17 | February | 18 | 0 | 1 | 19
Sprint 4 | Team 1 | 2026-02-18 | 2026-03-03 | March | 92 | 13 | 85 | 177
Sprint 4 | Team 2 | 2026-02-18 | 2026-03-03 | March | 44 | 13 | 7 | 51 | 5
Sprint 4 | Team 3 | 2026-02-18 | 2026-03-03 | March | 56 | 6 | 14 | 70
Sprint 4 | Team 4 | 2026-02-18 | 2026-03-03 | March | 23 | 5 | 2 | 25
Sprint 5 | Team 1 | 2026-03-04 | 2026-03-17 | March | 63 | 12 | 20 | 83
Sprint 5 | Team 2 | 2026-03-04 | 2026-03-17 | March | 22 | 4 | 9 | 31 | 5
Sprint 5 | Team 3 | 2026-03-04 | 2026-03-17 | March | 28 | 1 | 8 | 36
Sprint 5 | Team 4 | 2026-03-04 | 2026-03-17 | March | 14 | 4 | 0 | 14
Sprint 6 | Team 1 | 2026-03-18 | 2026-03-31 | March | 38 | 8 | 7 | 45
Sprint 6 | Team 2 | 2026-03-18 | 2026-03-31 | March | 13 | 7 | 1 | 14 | 5
Sprint 6 | Team 3 | 2026-03-18 | 2026-03-31 | March | 13 | 4 | 12 | 25
Sprint 6 | Team 4 | 2026-03-18 | 2026-03-31 | March | 29 | 1 | 0 | 29
Q2 Sprint 1 | Team 1 | 2026-04-01 | 2026-04-14 | April | 83 | 27 | 11 | 94
Q2 Sprint 1 | Team 2 | 2026-04-01 | 2026-04-14 | April | 38 | 11 | 2 | 40
Q2 Sprint 1 | Team 3 | 2026-04-01 | 2026-04-14 | April | 57 | 0 | 8 | 65
Q2 Sprint 1 | Team 4 | 2026-04-01 | 2026-04-14 | April | 20 | 1 | 1 | 21
Q2 Sprint 2 | Team 1 | 2026-04-15 | 2026-04-28 | April | 11 | 0 | 46 | 57
Q2 Sprint 2 | Team 2 | 2026-04-15 | 2026-04-28 | April | 35 | 4 | 8 | 43
Q2 Sprint 2 | Team 3 | 2026-04-15 | 2026-04-28 | April | 24 | 1 | 3 | 27
Q2 Sprint 2 | Team 4 | 2026-04-15 | 2026-04-28 | April | 14 | 0 | 0 | 14
Q2 Sprint 3 | Team 1 | 2026-04-29 | 2026-05-12 | May | 14 | 0 | 15 | 29
Q2 Sprint 3 | Team 2 | 2026-04-29 | 2026-05-12 | May | 59 | 24 | 23 | 82
Q2 Sprint 3 | Team 3 | 2026-04-29 | 2026-05-12 | May | 34 | 4 | 3 | 37
Q2 Sprint 3 | Team 4 | 2026-04-29 | 2026-05-12 | May | 21 | 2 | 0 | 21
Q2 Sprint 4 | Team 1 | 2026-05-13 | 2026-05-26 | May | 40 | 14 | 27 | 67
Q2 Sprint 4 | Team 2 | 2026-05-13 | 2026-05-26 | May | 57 | 6 | 16 | 73
Q2 Sprint 4 | Team 3 | 2026-05-13 | 2026-05-26 | May | 13 | 0 | 1 | 14
Q2 Sprint 4 | Team 4 | 2026-05-13 | 2026-05-26 | May | 4 | 0 | 4 | 8
Q2 Sprint 5 | Team 1 | 2026-05-27 | 2026-06-09 | June | 32 | 7 | 62 | 94
Q2 Sprint 5 | Team 2 | 2026-05-27 | 2026-06-09 | June | 53 | 17 | 17 | 70
Q2 Sprint 5 | Team 3 | 2026-05-27 | 2026-06-09 | June | 34 | 1 | 4 | 38
Q2 Sprint 5 | Team 4 | 2026-05-27 | 2026-06-09 | June | 13 | 0 | 0 | 13

## Team Median Input
Sprint ID | Sprint Start Date | Sprint End Date | Team | Month | BA to Dev | Median Cycle Time (days) - Dev to Test | Median Cycle Time (days) - Test to Acceptance | Median Cycle Time (days) - Acceptance to Done | Median Cycle Time (days) | Baseline Cycle Time | Δ vs Baseline | Δ% vs Baseline
Sprint 1 | 2026-01-07 | 2026-01-20 | Team 2 | January |  | 4.3 | 0.6 | 0.01 | 5.3 | 5.8 | -0.5 | -8.621%
Sprint 2 | 2026-01-21 | 2026-02-03 | Team 2 | February |  | 6.2 | 2.2 | 0.23 | 7.11 | 0 | 7.11
Sprint 3 | 2026-02-04 | 2026-02-17 | Team 2 | February |  | 5.7 | 0.7 | 0.3 | 5.16 | 0 | 5.16
Sprint 4 | 2026-02-18 | 2026-03-03 | Team 2 | March |  | 2.6 | 1.2 | 0.3 | 4.3 | 0 | 4.3
Sprint 1 | 2026-01-07 | 2026-01-20 | Team 3 | January |  | 7.2 | 7.4 | 0.3 | 7.4 | 5.1 | 2.3 | 45.1%
Sprint 2 | 2026-01-21 | 2026-02-03 | Team 3 | February |  | 5.5 | 4.5 | 0.4 | 6 | 5.1 | 0.9 | 17.65%
Sprint 3 | 2026-02-04 | 2026-02-17 | Team 3 | February |  | 1.22 | 1.15 | 0.3 | 2.4 | 5.1 | -2.7 | -52.94%
Sprint 4 | 2026-02-18 | 2026-03-03 | Team 3 | March |  | 2.1 | 4.2 | 0.1 | 4.13 | 5.1 | -0.97 | -19.02%
Sprint 1 | 2026-01-07 | 2026-01-20 | Team 4 | January |  | 6.1 | 3.8 | 2.5 | 5.4 | 4.7 | 0.7 | 14.89%
Sprint 2 | 2026-01-21 | 2026-02-03 | Team 4 | February |  | 0.16 | 3.6 | 2.4 | 4.1 | 4.7 | -0.6 | -12.77%
Sprint 3 | 2026-02-04 | 2026-02-17 | Team 4 | February |  | 1.12 | 1.21 | 1.21 | 3.23 | 4.7 | -1.47 | -31.28%
Sprint 4 | 2026-02-18 | 2026-03-03 | Team 4 | March |  | 4.19 | 1.22 | 1 | 4.2 | 4.7 | -0.5 | -10.64%
Sprint 1 | 2026-01-07 | 2026-01-20 | Team 1 | January | 0.1 days | 3.15 | 1.13 | 0.15 | 3.18 | 4 | -0.82
Sprint 2 | 2026-01-21 | 2026-02-03 | Team 1 | February | 0.1 days | 3.2 | 2.19 | 1.7 | 4.13 | 4 | 0.13
Sprint 3 | 2026-02-04 | 2026-02-17 | Team 1 | February | 2.23 days | 3.1 | 1.9 | 0.1 | 4.1 | 4 | 0.1
Sprint 4 | 2026-02-18 | 2026-03-03 | Team 1 | March | 1.2 days | 3.15 | 0.15 | 0.9 | 4.7 | 4 | 0.7
Sprint 5 | 2026-03-04 | 2026-03-17 | Team 1 | March |  | 4.12 | 1.14 | 0.18 | 5.23
Sprint 5 | 2026-03-04 | 2026-03-17 | Team 2 | March |  | 5.3 | 1 | 1.37 | 5.3
Sprint 5 | 2026-03-04 | 2026-03-17 | Team 3 | March |  | 7.1 | 4.19 | 0.22 | 7.2
Sprint 5 | 2026-03-04 | 2026-03-17 | Team 4 | March |  | 3.6 | 3.5 | 2.6 | 5.1
Sprint 6 | 2026-03-18 | 2026-03-31 | Team 1 | March |  | 3.1 | 1.4 | 1 | 4.6
Sprint 6 | 2026-03-18 | 2026-03-31 | Team 2 | March |  | 4.1 | 3.8 | 1.13 | 5.23
Sprint 6 | 2026-03-18 | 2026-03-31 | Team 3 | March |  | 5.23 | 6.2 | 0.65 | 7.2
Sprint 6 | 2026-03-18 | 2026-03-31 | Team 4 | March |  | 4.2 | 3.3 | 3.8 | 7.1
Q2 Sprint 1 | 2026-04-01 | 2026-04-14 | Team 1 | April |  | 4.3 | 1.3 | 0.2 | 4.17
Q2 Sprint 1 | 2026-04-01 | 2026-04-14 | Team 2 | April |  | 6.1 | 4.1 | 2.1 | 8.2
Q2 Sprint 1 | 2026-04-01 | 2026-04-14 | Team 3 | April |  | 5.1 | 3.1 | 1.4 | 4.17
Q2 Sprint 1 | 2026-04-01 | 2026-04-14 | Team 4 | April |  | 1.1 | 1.2 | 1.2 | 2.2
Q2 Sprint 2 | 2026-04-15 | 2026-04-28 | Team 1 | April |  | 1.5 | 1.2 | 0.19 | 2.6
Q2 Sprint 2 | 2026-04-15 | 2026-04-28 | Team 2 | April |  | 3.2 | 1.5 | 5.2 | 4.1
Q2 Sprint 2 | 2026-04-15 | 2026-04-28 | Team 3 | April |  | 3.22 | 3.1 | 4.3 | 6
Q2 Sprint 2 | 2026-04-15 | 2026-04-28 | Team 4 | April |  | 3.2 | 2.7 | 1.3 | 4.7
Q2 Sprint 3 | 2026-04-29 | 2026-05-12 | Team 1 | May |  | 3.2 | 1.1 | 1.1 | 5.2
Q2 Sprint 3 | 2026-04-29 | 2026-05-12 | Team 2 | May |  | 6 | 2.5 days | 3.1 | 6 days
Q2 Sprint 3 | 2026-04-29 | 2026-05-12 | Team 3 | May |  | 4.2 | 4.3 | 1.2 | 4.2
Q2 Sprint 3 | 2026-04-29 | 2026-05-12 | Team 4 | May |  | 0.2 | 2.1 | 1.2 | 3.1
Q2 Sprint 4 | 2026-05-13 | 2026-05-26 | Team 1 | May |  | 5.2 | 1.4 | 0.15 | 5.2
Q2 Sprint 4 | 2026-05-13 | 2026-05-26 | Team 2 | May |  | 2.15 | 1.22 | 3.43 | 2.18
Q2 Sprint 4 | 2026-05-13 | 2026-05-26 | Team 3 | May |  | 7.2 | 3.6 | 0.25 | 7.13
Q2 Sprint 4 | 2026-05-13 | 2026-05-26 | Team 4 | May |  | 2.4 | 1.12 | 1 | 6.7
Q2 Sprint 5 | 2026-05-27 | 2026-06-09 | Team 1 | June |  | 3.7 | 1.9 | 0.2 | 5.1
Q2 Sprint 5 | 2026-05-27 | 2026-06-09 | Team 2 | June |  | 6.1 days | 5.1 days | 1.1 days | 7.15 days
Q2 Sprint 5 | 2026-05-27 | 2026-06-09 | Team 3 | June |  | 7.5 days | 2.1 days | 1.2 days | 7.2 days
Q2 Sprint 5 | 2026-05-27 | 2026-06-09 | Team 4 | June |  | 3.22 days | 2.3 days | 1.7 days | 9.17 days

## FTPR
First Time Pass Rate
Sprint ID | Team | Sprint Start Date | Sprint End Date | Month | Total Stories Completed | Total Stories Completed with Defects | Total Stories Completed w/o any Defects | FTPR | Stories number having defects (1 or more)
Sprint 6 | Team 1 | 2026-03-18 | 2026-03-31 | March | 30 | 3 | 27 | 90 | LIFE-21009,LIFE-21019,LIFE-24870
Sprint 6 | Team 2 | 2026-03-18 | 2026-03-31 | March | 18 | 4 | 14 | 77.7778 | LIFE-26359,LIFE-26114,LIFE-25622,LIFE-24871
Sprint 6 | Team 3 | 2026-03-18 | 2026-03-31 | March | 8 | 2 | 6 | 75 | LIFE-26840,LIFE-25711
Sprint 6 | Team 4 | 2026-03-18 | 2026-03-31 | March | 21 | 1 | 20 | 95.2381 | LIFE-26564
Sprint 5 | Team 1 | 2026-03-04 | 2026-03-17 | March | 53 | 10 | 43 | 81.1321 | LIFE-17329,LIFE-17374,LIFE-17449,LIFE-21003,LIFE-21021,LIFE-21998,LIFE-24407,LIFE-25566,LIFE-25612,LIFE-26159,
Sprint 5 | Team 2 | 2026-03-04 | 2026-03-17 | March | 17 | 3 | 14 | 82.3529 | LIFE-25829,LIFE-25840,LIFE-26259
Sprint 5 | Team 3 | 2026-03-04 | 2026-03-17 | March | 11 | 1 | 10 | 90.9091 | LIFE-22140
Sprint 5 | Team 4 | 2026-03-04 | 2026-03-17 | March | 17 | 0 | 17 | 100
Q2 Sprint 1 | Team 1 | 2026-04-01 | 2026-04-14 | April | 45 | 22 | 23 | 51.1111 | LIFE-6512,LIFE-8983,LIFE-21016,LIFE-21011,LIFE-22466,LIFE-23241,LIFE-23687,LIFE-23719,LIFE-23740,LIFE-23765,LIFE-23914,LIFE-23921,LIFE-24028,LIFE-24077
Q2 Sprint 1 | Team 2 | 2026-04-01 | 2026-04-14 | April | 24 | 7 | 17 | 70.8333 | LIFE-27961,LIFE-27233,LIFE-25859,LIFE-25082,LIFE-25078,LIFE-24556,LIFE-24343,LIFE-24078
Q2 Sprint 1 | Team 3 | 2026-04-01 | 2026-04-14 | April | 17 | 0 | 17 | 100
Q2 Sprint 1 | Team 4 | 2026-04-01 | 2026-04-14 | April | 33 | 1 | 32 | 96.9697 | LIFE-26649
Q2 Sprint 2 | Team 1 | 2026-04-15 | 2026-04-28 | April | 16 | 4 | 12 | 75 | LIFE-26681,LIFE-25824, LIFE-25119, LIFE-6757
Q2 Sprint 2 | Team 2 | 2026-04-15 | 2026-04-28 | April | 30 | 3 | 27 | 90 | LIFE-26125, LIFE-25549, LIFE-24988
Q2 Sprint 2 | Team 3 | 2026-04-15 | 2026-04-28 | April | 7 | 0 | 7 | 100
Q2 Sprint 2 | Team 4 | 2026-04-15 | 2026-04-28 | April | 20 | 0 | 20 | 100
Q2 Sprint 3 | 2026-04-29 | 2026-05-12 | Team 1 | May | 14 | 3 | 11 | 78.5714 | LIFE-25820,LIFE-22849,LIFE-22848
Q2 Sprint 3 | 2026-04-29 | 2026-05-12 | Team 2 | May | 48 | 17 | 31 | 64.5833 | LIFE-26956,LIFE-27035,LIFE-24719,LIFE-26957,LIFE-28229,LIFE-26764,LIFE-19690,LIFE-18830,LIFE-27096,LIFE-26958,LIFE-26765,LIFE-26756,LIFE-26763,LIFE-15809,LIFE-26767,LIFE-28532,LIFE-15801
Q2 Sprint 3 | 2026-04-29 | 2026-05-12 | Team 3 | May | 15 | 2 | 13 | 86.6667 | LIFE-26869,LIFE-6861
Q2 Sprint 3 | 2026-04-29 | 2026-05-12 | Team 4 | May | 30 | 2 | 28 | 93.3333 | LIFE-28965,LIFE-27172
Q2 Sprint 4 | 2026-05-13 | 2026-05-26 | Team 1 | May | 28 | 3 | 25 | 89.2857 | LIFE-24349,LIFE-24345,LIFE-6758
Q2 Sprint 4 | 2026-05-13 | 2026-05-26 | Team 2 | May | 29 | 6 | 23 | 79.3103 | LIFE-29960,LIFE-29957,LIFE-29952,LIFE-28976,LIFE-26957,LIFE-19690
Q2 Sprint 4 | 2026-05-13 | 2026-05-26 | Team 3 | May | 4 | 0 | 4 | 100
Q2 Sprint 4 | 2026-05-13 | 2026-05-26 | Team 4 | May | 12 | 0 | 12 | 100
Q2 Sprint 5 | 2026-05-27 | 2026-06-09 | Team 1 | June | 25 | 8 | 17 | 68 | LIFE-31123,LIFE-30286,LIFE-27867,LIFE-26040,LIFE-25822,LIFE-25113,LIFE-24734,LIFE-24361
Q2 Sprint 5 | 2026-05-27 | 2026-06-09 | Team 2 | June | 35 | 12 | 23 | 65.7143 | LIFE-29958,LIFE-29956,LIFE-29954,LIFE-29504,LIFE-29499,LIFE-29497,LIFE-28320,LIFE-28314,LIFE-26956,LIFE-26555,LIFE-26119,LIFE-23970
Q2 Sprint 5 | 2026-05-27 | 2026-06-09 | Team 3 | June | 12 | 1 | 11 | 91.6667 | LIFE-20339
Q2 Sprint 5 | 2026-05-27 | 2026-06-09 | Team 4 | June | 30 | 0 | 30 | 100

## Backlog (hidden)
Backlog Summary
Team | EPIC | Release | Feature | Total Stories | Total Story Points | Groomed | Spike | Notes
Team 1 | Prod-199 | June

## EAC Notes (hidden)
Monthly burn variance shows how we performed financially this month, while Estimate at Completion shows where we are projected to land financially at the end of the program.
EAC = Money already spent + Forecast remaining cost
Example Item Amount Spent so far $2.5M Remaining forecast $2.8M EAC $5.3M
Usually caused by: rework poor estimation scope creep low productivity
EAC tells leadership: ✅ Is the vendor financially under control? ✅ Will we overspend before project ends? ✅ Are estimates realistic? ✅ Is scope or rework increasing cost? It is a forward-looking health indicator.

## Disussion Points (hidden)
Metrics | Inputs
ETC | Refined backlog for next 1 quarter
Cost per SP | How to calculate cost for ERIE and Innova for overall ETC and cost per sprint/point
Rework effort | Assign points/complexity to defect to determine ave rework effort
Cycle Time (Median) | Establish baseline from JIRA for SP1, SP2 etc

## Monthly Burn Variance Reasons (hidden)
Monthly Cost Variance
Category
Rework
Depedency Delay
Scope Changes
Staffing

## Risks_Decisions_Improvements
Date | Category | Details | Updates | Owner | ETA | Status
2026-06-03 | Improvement | QA team cross skilling across all the sprint teams | QA team got trained in Illustration/Premium/Pricing Testing/Uwpro/Downstream Batch processing/Billing and other relevant topics
2026-05-12 | Improvement | Complete the Applitool Scripts for automatic regression of the forms | 14 Scripts are prepared and run to support the Release 1.1 | Ashish/Veera/Ananth | 2026-05-19 | Completed
2026-05-05 | Improvement | Implement a formal and manually gated print code review process | Nowsheen is leading the Print code review with support from Melinda and CK. | Nowsheen | 2026-05-12 | Completed
2026-05-05 | Improvement | Plan for In-Sprint automation for missed story cards from past sprints - Team 1 and Team 3 for Release 1.1 | Team 1 (2 Hours) LIFE-28764 - LifeWeb - Other Insurance and Replacement Screen - 1st Question Displayed Incorrectly LIFE-28410- Other Insurance and Replacement Screen - New Question Team 3 (2 hours) LIFE-27290- Taxonomy Changes - EFL Money to EFL Billing | Manish/Arun/Karthik/Joy | 2026-05-12 | Completed
2026-05-08 | Improvement | First time pass rate has been consistently low specially for team 1 and team 2. | Need to strengthen the process - pre-amigo, smaller story cards etc. this will be an ongoing activity unless we see improve FTPR to 95% | Karthik/Melinda/Abhijit | 2026-06-30 | WIP
2026-05-05 | Improvement | Provided 212 UAT policies (60 policies premium testing, 60 policies commission, 65 policies Dade pay testing, 12 portal testing, 15 forms content validation testing) to business team so far that would have taken at least 70 hours (20 mins/per policy) |  | Ashish/Veera/Ananth | Ongoing | WIP
2026-06-19 | Decision | Pavan Bhubathiraju ( Integration Developer) Role Closure | Pavan has worked only on couple of cards in last few sprints. He is also aspiring to move onto other areas of work. We believe he is not being fully utilized and the role can be closed | Joy/Nick | 2026-07-03 | WIP
2026-06-18 | Decision | Progressing with the agreed Addendum | Its discussed and shared over email | Joy | 2026-06-26 | Completed
2026-06-22 | Decision | Approval to have Sandip Banala as Vaishnavi's replacement as Sadhu Dharani as Mendix buffer in the team | Vaishnavi has resigned last week | Joy | 2026-06-26 | Completed
2026-06-03 | Decision | Need a decision on Shivani Yandra's billability - she was supposed to replacement for Sushanth Merugu and join team 1. SVP Approval pending since 4/27 | Chrystal following up with Joy | Joy/Nick/Subrata | 2026-06-05 | Completed
2026-04-08 | Decision | Raja, Bharat and Subbu are planned to be released by 6/28 per SOW. With full rollout moving to June and we expect some enhancement post rollout so do we expect to extend their contract? We may have to extend it until Q3 for Subbu/Bharat and end of year for Raja? | Subbu can be roll off. 6/24 Final Expense, 6/18 Reinstatement, 6/4 Wholelife, 7/16 - Misc, Conversion - Tentative Sept. Karthik/Joy to connect and come back for Bharat by 5/22. Raja to keep it until end of Sept. | Joy/Karthik | 2026-05-22 | Open
2026-03-25 | Decision | Improve collaboration and partnership with Sapiens team. Avoid escalation unless absolutely necessary. Document has been put in place | Joy informed Brian that QA will put note in Sapiens Defect if anything is missing to avoid any concern. All QA's are part of Sapiens call. Pending Item - File testing is in progress so learning curve will be there while running new batches. | Nick/Joy | 2026-03-25 | Closed
2026-03-25 | Decision | Moving code to Test PS for term as most of the term work was completed to continue with downstream validation because of active development in Test A for whole life/re-instatement and uncovering unexpected blockers | Term code moved to Test PS | Melinda/Karthik/Joy | 2026-04-03 | Closed
2026-03-25 | Decision | Team 1 assign story points to standalone defects to determine the effort but other teams don’t follow this and keep 0 points. We need alignment and determine the consistent approach across teams | Joy will work with all Scrum Masters on this | Joy |  | Closed
2026-03-25 | Decision | Should team look at baseline velocity vs total points planned for Sprint Commitment? | Team aligned to use baseline velocity for sprint commitment | Joy | 2026-03-25 | Closed
2026-06-03 | Risk | Down times due to and following Sapiens Deployment are impacting hours of Testing Window ( e.g., 5/27, 5/29, 6/1) | Enforce a more robust smoke testing and shorter deployment window for Sapiens | Corey/Joy | 2026-06-15 | Open
2026-05-19 | Risk | The bi-weekly release cycle since term pilot is creating conflicting capacity prioritization between in-sprint work ( Full roll-out,whole life , reinstatement etc), Defect retests for release cycles, whole life E2E plan, E2E execution and regression cycles for the release & UAT support and in sprint automation effort. This can potentially slow down the progress to whole life and full-roll out | Team assessing the possibility of bringing in more automation in regression. Also discuss the risk with Erie Leadership for possible options and approaches | Arun/Karthik/Joy/Nick | TBD | WIP
2026-05-19 | Risk | Frequently different versions of CoreSuite codes between Test and Prod and even within Test environment through different periods of Testing due to the weekly release schedule potentially blocking or slowing down the Regression activities and reducing the integrity of the testing | Corey is working with Sapiens on the release roadmap | Corey/Karthik | TBD | WIP
2026-04-08 | Risk | Downstream testing, file testing, and PHS testing are at risk due to automated batches not yet enabled in TestPS | Meeting is being setup with PPS to automate batches at the earliest | Corey/Manish | 2026-04-14 | Closed
2026-03-25 | Risk | known Risk - Whole life Sapiens cards/defects are planned for 4/20 (Sprint 12) release putting risk for pilot. | Team decided to move forward with Term only for pilot so we are good | Joy/Nick | 2026-04-01 | Closed
2026-03-25 | Risk | Known Risk - About 25+ interface files to be validated part of E2E - File development (3 CRs + Infogix) pending with Sapiens needed for pilot and rest files need to be tested/validated by business | Corey is setting up time with business/QA for working session for pending validation files and Joy following up with Sapiens for the update | Joy/Corey/Manish/Karthik |  | Closed
2026-03-25 | Risk | Unexpected downtime impacting E2E testing (Sapiens, UWPro, Tempus etc) being tracked and actions are being taken | This will be ongoing tracking to notice any unplanned outage and take actions | Manish/Karthik/Melinda/Arun |  | Closed
2026-04-08 | Improvement | Automation Handbook drafting is in progress | keeping the completion date as 4/17 to include API part and code movement/branching/approval process | Ashish/Bharat/Karthik | 2026-05-15 | WIP
2026-04-08 | Improvement | Started 5 why analysis to reduce the rework ratio for SP6 defects. Expecting the action to be taken that helps to reduce the rework effort |  | Karthik/Melinda/Manish/Arun | Ongoing | WIP
2026-04-08 | Improvement | Working with Melinda to generate data models (Logical/Physical) for AWS purge project | Initial results are shared with Manoj. Review and refinement may be needed after the review. | Melinda/Manoj | 2026-04-14 | Completed
2026-03-25 | Improvement | Both UI and API smoke/regression suites are scheduled daily (Test A/Test PS) to track and reason for failure |  | Ashish/Bharat |  | Completed
2026-03-25 | Improvement | Improvement in Automation code quality and stability as team updated the code to the new framework version and fixed the issues. |  | Ashish |  | Completed
2026-03-25 | Improvement | Improving quality by enabling gated (30%) pipeline for Test A/PS | Seeing about 60% pass rate past few build in TestPS. | Karthik/Ashish/Melinda/Mateen | 2026-03-27 | Completed
2026-04-08 | Improvement | QA Team completed ChatGPT pilot for test case design with Team 2 with the help of Karthik and noticed 30% estimated design savings. | Implementation is in progress for Team 2 story cards to see the efficiency and saving at scale | Manish/Arun/Karthik | 2026-04-10 | Completed
2026-03-25 | Improvement | Daily testing report involve lot of manual effort, prone to error. Looking for semi-automate the report in JIRA | Planned for Release 1.1 | Purush |  | WIP
2026-03-25 | Decision | Explore and plan ahead on tentative card delivery dates across teams by Developers to avoid spillover |  | Melinda/Joy |  | TBD
2026-03-25 | Improvement | Strong overlap between Onsite and Offshore served us well in the winter, many supported late EST afternoon for direct interaction with ERIE |  | Arunava/Manish |  | Completed
2026-03-25 | Improvement | Frequent connect is in place with ERIE leads (Abhishek, Karthik, Melinda, Abhijit) for concern, feedback and improvement |  | Manish/Arun |  | Completed

## Prod Leakage Details (hidden)
Release | Problem | Impact | Urgency | Priority | Description | Root cause | Action Item
March'26 | PRB0068481 | Low | Medium | 4-Low | Inflight scenarios failed in Prod | code fix was made to conversion which had impact to new business flow but impact analysis was not done so inflight NB scenarios were not re-executed | Developer/QA work together end of testing, review defects, perform impact analysis and plan the manual regression along with automated regression
March'26 | PRB0068596 | Low | Low | 5-Planning | non-life agent able to issue EEL policy | Service change (MDM to ASR) - Code was copied from TUW but didn’t have unit test cases covered and understanding of the scope/code | Non-life agent testing will be added part of regression for every release
March'26 | PRB0068645 | Medium | Low | 4-Low | Error for Life License (Recent release issue to update a constant missed) | MDM pointing to Stage instead of prod (constant/env change) but was not added in the dev checklist | TBD
Please refer to the Quality tab post March data